## Roadmap
| 2026-01-05 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33 | Sprint 34 | Sprint 35 | Sprint 36 | Sprint 37 | Sprint 38 | Sprint 39 | Sprint 40 | Sprint 41 | Sprint 42 | Sprint 43 | Sprint 44 | Sprint 45 | Sprint 46 | Sprint 47 | Sprint 48 | Sprint 49 | Sprint 50 | Sprint 51 | Sprint 52 | Sprint 53 | Sprint 54 | Sprint 55 | Sprint 56 | Sprint 57 | Sprint 58 | Sprint 59 | Sprint 60 | Sprint 61 | Sprint 62 | Sprint 63 | Sprint 64 | Sprint 65 | Sprint 66 | Sprint 67 | Sprint 68 | Sprint 69 | Sprint 70 | Sprint 71 | Sprint 72 | Sprint 73 | Sprint 74 | Sprint 75 | Sprint 76 | Sprint 77 | Sprint 78 | Sprint 79 | Sprint 80 | Sprint 81 | Sprint 82 | Sprint 83 | Sprint 84 | Sprint 85 | Sprint 86 | Sprint 87 | Sprint 88 | Sprint 89 | Sprint 90 | Sprint 91 | Sprint 92 | Sprint 93 | Sprint 94 | Sprint 95 | Sprint 96 | Sprint 97 | Sprint 98 | Sprint 99 | Sprint 100 | Sprint 101 | Sprint 102
| W49 | W50 | W51 | W52 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43
 | time axis 2024-12-02 to 2025-10-20
 | time axis 2024-12-06 to 2025-10-24
DevCrew #1 (2-dev team) | 2024-12-06: Onboarding; 2024-12-13: Azure Landing Zone Baseline (Subscriptions, Entra ID with GCP SSO, RBAC); 2024-12-20: Azure Infrastructure Deployment (Networking, Storage, ACR, Service Bus, EventHubs, CosmosDB, AKS Cluster, DNS Zones); 2025-01-03: Azure VPN Setup with OpenVPN; 2025-01-10: AKS Cluster Setup (Helm Charts, Add-ons, adapt to deploy in Azure); 2025-01-24: Configure build pipelines to publish images to ACR; 2025-01-31: Azure Databricks Workspace setup & configuration; 2025-02-14: Configure Snowflake and DBT in Azure Databricks. Deploy data workloads; 2025-02-28: Testing, Feedback, Stabilization
|  | Setup Deployment Pipelines (Terraform, GitHub Actions) |  | Messaging Services Replacement Kafka->Event Hubs RabbitMQ -> Service Bus (Codebase remains as-is) |  | AWS ArgoCD - Configuration for deployment to Azure | Adapt codebase to consume Azure services (Service Bus, Blob Storage, others) |  | Athena PG and Midgar PG deployment in Azure Database for PostgreSQL | OpenAI Models Deployment | Connect Databricks with Azure dependencies (Azure Storage, RabbitMQ through Service Bus)
|  |  | TOTAL FT WEEKS | 12
|  |  | FT Price | 196800
|  |  | DevCrew Price | 75000

## Roadmap (old) (hidden)
| 2025-07-07 | 2025-07-18 | 2025-07-25 | 2025-08-01 | 2025-08-08 | 2025-08-15 | 2025-08-22 | 2025-08-29 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27 | Sprint 28 | Sprint 29 | Sprint 30 | Sprint 31 | Sprint 32 | Sprint 33 | Sprint 34 | Sprint 35 | Sprint 36 | Sprint 37 | Sprint 38 | Sprint 39 | Sprint 40 | Sprint 41 | Sprint 42 | Sprint 43 | Sprint 44 | Sprint 45 | Sprint 46
| W49 | W50 | W51 | W52 | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43
 | time axis 2024-12-02 to 2025-10-20
 | time axis 2024-12-06 to 2025-10-24
|  | M#1 - Azure Infrastructure | [6 empty] | M#2 - Cost & Performance Optimization and GRC Strategy |  |  |  | M#3 - AWS to Azure Customer Migration Strategy |  |  |  |  | M#4 - Execute Customer Migration from AWS to Azure
Fireteam #1 (3-dev team) | 2024-12-06: Onboarding; 2024-12-13: Understand current Azure architecture, compare it with AWS; 2024-12-20: Azure Landing Zone (Management Groups, Subscriptions, RBAC, Network Topology, DNS, Routing); 2025-01-03: Modify Terraform/OpenTofu code for deploying services in Azure; 2025-01-24: Replace AWS services not available in Azure (e.g.: Cert Manager); 2025-01-31: Identify cost improvement opportunities and implement changes (includes spikes/POCs); 2025-02-14: Execute performance testing, implement fixes/modifications to address performance issues; 2025-02-28: Implement cloud-to-cloud connectivity (S2S VPN, ExpressRoute); 2025-03-07: Design and implement data migration strategy for all relevants data stores (Aurora, S3, Databricks); 2025-03-21: Execute migration dry-run for representative customer; adjust based on findings; 2025-04-04: Migrate customers from AWS to Azure Work with Altana to validate that the solution is working as expected Monitor platform, both during the migration and after it's completed
[5 empty] | Modify application deployment scripts (Kubernetes, AzFunc, others) |  |  | Deploy Databricks in Azure OR Connect with Databricks in AWS | Configure Azure Policies (FedRAMP High, DoD IL5) | Iterate over Azure Policies findings; fix issues or mark them as false positives with justification |  |  | Identify compute and data components involved in the migration | Implement scripts for migrating services and applications (deployment in AKS and AzFunc, among others) |  | Implement traffic shifting from AWS to Azure | Design migration rollback plan
x

## Sheet1 (hidden)
Signal Scienses as Firewall
They have it as a module in nginx
They are not considering going out of it in the short term
CDN Not Mandatory
Kafka, need to explore
Functions -> Containers
Azure Batch